## Documentation
Canvas Scribe
Author
Date
Purpose | To estimate the production schedule for a new game to be released by Canvas Scribe

## Production Schedule
Canvas Scribe
Production Schedule for Escape from Dunkirk
Summary
Start Date
Release Date
Total Working Days
Total Calendar Days
Phase | Start Date | End Date | Workdays to Complete | Phase Starts |  | Holidays
Idea Development |  |  | 10 | 0 | Start Date | 2021-01-01
Story Writing | 1900-01-01 |  | 15 | 1 | workday after the Idea Development end date | 2021-01-18
Character/Visual Design | 1900-01-01 |  | 45 | 1 | workday after the Story Writing end date | 2021-05-31
Initial Story Boarding | 1900-01-01 |  | 45 | 1 | workday after the Story Writing end date | 2021-07-04
Story Boarding Final Edits | 1900-01-01 |  | 35 | 1 | workday after the Initial Story Boarding end date | 2021-09-06
Digital Animation | 1900-01-01 |  | 75 | 1 | workday after the Story Boarding Final Edits end date | 2021-11-25
Rough Sound | 1900-01-01 |  | 15 | 1 | workday after the Story Boarding Final Edits end date | 2021-11-26
Backgrounds | 1900-01-02 |  | 75 | 2 | workdays after the Character/Visual Design end date | 2021-12-24
Character Animation | 1900-01-02 |  | 75 | 2 | workdays after the Character/Visual Design end date | 2021-12-25
Initial Animation Effects | 1900-01-02 |  | 55 | 2 | workdays after the Rough Sound end date | 2021-12-31
Cleanup Animation Effects | 1900-01-01 |  | 15 | 1 | workday after the Initial Animation Effects end date | 2022-01-01
Digital Coloring | 1900-02-02 |  | 80 | 25 | workdays after the Initial Storyboarding end date | 2021-01-17
First Edit | 1900-01-01 |  | 10 | 1 | workday after the Cleanup Animation Effects end date | 2022-05-30
Testing | 1900-01-01 |  | 20 | 1 | workday after the First Edit end date | 2022-07-04
Revisions | 1900-01-01 |  | 20 | 1 | workday after the Testing end date | 2022-09-05
Second Testing | 1900-01-01 |  | 10 | 1 | workday after the Revisions end date | 2022-11-24
Final Approval | 1900-01-01 |  | 5 | 1 | workday after the Second Testing end date | 2022-11-25
Production | 1900-01-01 |  | 20 | 1 | workday after the Final Approval end date | 2022-12-24
Release | 1900-01-01 |  | 0 | 1 | workday after the Production end date | 2022-12-25
2022-12-31
Formulas:
Start Date = WORKDAY([End Date, row above],[Phase Starts],H10:H29)
Start Date = WORKDAY(C11,[Phase Starts],H10:H29)