## Slide 1
Resource Planning
Dr. Narpat Ram Sangwa
Assistant Professor
Operations & Supply Chain Management
IIM Sirmaur

## Slide 2: Learning Objectives
How much of an item is needed to meet demand?
What are the various parts and components required?
When to order parts and components?

## Slide 3: Resource planning
MRP – Material
Requirements
Planning
MRP II – Manufacturing
Resource Planning
ERP- Enterprise Resource Planning

## Slide 4: Material Requirements Planning
Materials requirements planning (MRP) is a computerized inventory planning and control system for determining when (no earlier and no later) and how many of each of the parts, components, and materials should be ordered or produced.
It translates master schedule requirements of end items into time-phased requirements for subassemblies, components and raw materials.

## Slide 5: Demand Characteristics
Independent Demand
(i.e. Finished goods)
A
B(4)
C(2)
D(2)
E(1)
D(3)
F(2)
Dependent Demand
(i.e. Components of finished goods)
Independent demand is uncertain. Dependent demand is certain.
Dependent demand drives MRP.

## Slide 6: Demand Characteristics
1 2 3 4 5
Week
400 –
300 –
200 –
100 –
No. of tables
Continuous demand
M T W Th F M T W Th F
400 –
300 –
200 –
100 –
No. of tables
Discrete demand
Independent demand
100 tables
Dependent demand
100 x 1 =
100 tabletops
100 x 4 = 400 table legs

## Slide 7: MRP Core Concepts
Dependent Demand
Production (or procurement) of parts and materials is directly linked to demand for the final product
Time-phased Scheduling
Parts and components must be ordered in advance to accommodate lead times between order placement and receipt

## Slide 8: Quick Review
True or False
Correct Answer: True
MRP is generally applicable to items with dependent demand.

## Slide 9: Quick Review
True or False
Correct Answer: False
A dependent demand item is so called because its demand is dependent on customer preferences.

## Slide 10: Quick Review
MCQ
Correct Answer: D
Dependent demand and independent demand items differ in that:
A) for any product, all components are dependent-demand items.
B) the need for independent-demand items is forecast.
C) the need for dependent-demand items is calculated.
D) All of the above are true.

## Slide 11: MRP Inputs and Outputs

## Slide 12: Master Production Schedule
The master production schedule (MPS), also called the master schedule, specifies which end items or finished products a firm is to produce, how many are needed, and when they are needed.
The master production schedule works within the constraints of the aggregate production plan but produces a more specific schedule by individual products.
The time frame is more specific, too.
The total length of time required to manufacture a product is called its cumulative lead time.

## Slide 13: Master Production Schedule
Drives MRP process with a schedule of finished products
Quantities represent production not demand
Quantities may consist of a combination of customer orders and demand forecasts
Quantities represent what needs to be produced, not what can be produced
Quantities represent end items that may or may not be finished products

## Slide 14: Aggregate Production Plan
Months January February
Aggregate Plan 1,500 1,200 (Shows the total quantity of amplifiers)
Weeks 1 2 3 4 5 6 7 8
Master Production Schedule (Shows the specific type and quantity of amplifier to be produced)
240-watt amplifier 100 100 100 100
150-watt amplifier 500 500 450 450
75-watt amplifier 300 100

## Slide 15: Product Structure File
Once the MPS is set, the MRP system accesses the product structure file to determine which component items need to be scheduled.
The product structure file contains a bill of material (BOM) for every item produced.
The bill of material for a product lists the items that go into the product, includes a brief description of each item, and specifies when and in what quantity each item is needed in the assembly process.

## Slide 16: Product Structure File
Bill of Materials
Level |  | Quantity
0 | Chair | 1
1 | Leg assembly | 1
2 | Legs | 2
2 | Cross bar | 1
1 | Seat | 1
1 | Back assembly | 1
2 | Side rails | 2
2 | Cross bar | 1
2 | Back supports | 3

## Slide 17: Product Structure File
Clipboard example

## Slide 18: Low-Level Coding
Restructuring the bill of materials so that multiple occurrences of a component all coincide with the lowest level at which the component occurs.

## Slide 19: BOM Example
B(2)
C(3)
1
E(2)
E(2)
F(2)
2
D(2)
D(2)
G(1)
3
Product structure for “Awesome” (A)
A
Level
0
Part B: 2 x number of As = (2)(50) = 100
Part C: 3 x number of As = (3)(50) = 150
Part E: 2 x number of Bs
+ 2 x number of Cs = (2)(100) + (2)(150) = 500
Part F: 2 x number of Cs = (2)(150) = 300
Part G: 1 x number of Fs = (1)(300) = 300
Part D: 2 x number of Bs
+ 2 x number of Fs = (2)(100) + (2)(300) = 800
For an order of 50 Awesome speaker kits

## Slide 20: Time-phased bills
A time-phased bill of material, also known as a time-phased assembly chart, is basically a horizontal product structure diagram that graphically shows the lead time required to purchase or manufacture an item.
An MRP system can forward schedule or backward schedule production.

## Slide 21: Time-phased bills Example

## Slide 22: Item Master File
The item master file, or inventory file, contains an extensive amount of information on every item that is produced, ordered, or inventoried in the system.
It includes data such as on-hand quantities, on-order quantities, lot sizes, safety stock, lead time, and past usage figures.
It provides a detailed description of the item, specifies the inventory policy, updates the physical inventory count, summarizes the item’s year-to-date or month-to-date usage, and provides internal codes to link this file with other related information in the MRP database.
This involves—
maintaining orderly stockrooms;
establishing and enforcing procedures for inventory withdrawal;
ensuring prompt and accurate entry of inventory transactions;
Taking physical inventory count on a regular basis; and
reconciling inventory discrepancies in a timely manner.

## Slide 23: Item Master File

## Slide 24: Quick Review
MCQ
Correct Answer: B
Firms making many different final products use ________ to facilitate production scheduling.
A) planning bills
B) modular bills
C) phantom bills
D) overdue bills

## Slide 25: Quick Review
True or False
Correct Answer: False
"Phantom bills" are bills of material for subassemblies that do not exist in reality.

## Slide 26: Quick Review
True or False
Correct Answer: True
The time-phased product structure, unlike the bill of material, adds the concept of lead times.

## Slide 27: The MRP process
The MRP process consists of four basic steps:
Exploding the bill of material,
Netting out inventory,
Lot sizing, and
Time-phasing requirements.
The process is performed again and again, moving down the product structure until all items have been scheduled.
Identifying information at the top of the matrix includes the item name or number, the lowest level at which the item appears in the product structure (called low level code or LLC),
The quantities in which an item is usually made or purchased (called lot size)

## Slide 28: MRP matrix

## Slide 29: Example— School mate products
School Mate offers a number of standard products to encourage writing outside of the classroom, including clipboards, lapdesks, lapboards, and pencil boxes. Rising costs and inventory levels have prompted the company to install a computerized planning and control system called MRP. The MPS and bill of material modules are up and running. Sample output follows. Before going live with the MRP module, School Mate has asked for a manual demonstration. Since manual calculations can be quite tedious, you have decided to prepare MRP matrices for only three items—the clipboard and lapdesk, and a common component, pressboard. The master production schedule, abbreviated product structure diagrams, and inventory information are given below.

## Slide 30: Example— School mate products

## Slide 31: Example— School mate products
ITEM: CLIPBOARD LLC: 0 PERIOD
LOT SIZE: L4L LT: 1 1 2 3 4 5
Gross Requirements 85 95 120 100 100
Scheduled Receipts 175
Projected on Hand 25
Net Requirements
Planned Order Receipts
Planned Order Releases
ITEM: CLIPBOARD LLC: 0 PERIOD
LOT SIZE: L4L LT: 1 1 2 3 4 5
Gross Requirements 85 95 120 100 100
Scheduled Receipts 175
Projected on Hand 25 115
Net Requirements 0
Planned Order Receipts
Planned Order Releases
(25 + 175) = 200 units available
(200 - 85) = 115 on hand at the end of Period 1
ITEM: CLIPBOARD LLC: 0 PERIOD
LOT SIZE: L4L LT: 1 1 2 3 4 5
Gross Requirements 85 95 120 100 100
Scheduled Receipts 175
Projected on Hand 25 115 20
Net Requirements 0 0
Planned Order Receipts
Planned Order Releases
115 units available
(115 - 95) = 20 on hand at the end of Period 2
ITEM: CLIPBOARD LLC: 0 PERIOD
LOT SIZE: L4L LT: 1 1 2 3 4 5
Gross Requirements 85 95 120 100 100
Scheduled Receipts 175
Projected on Hand 25 115 20 0
Net Requirements 0 0 100
Planned Order Receipts 100
Planned Order Releases 100
20 units available
(20 - 120) = -100 — 100 additional Clipboards are required
Order must be placed in Period 2 to be received in Period 3
ITEM: CLIPBOARD LLC: 0 PERIOD
LOT SIZE: L4L LT: 1 1 2 3 4 5
Gross Requirements 85 95 120 100 100
Scheduled Receipts 175
Projected on Hand 25 115 20 0 0 0
Net Requirements 0 0 100 100 100
Planned Order Receipts 100 100 100
Planned Order Releases 100 100 100
Following the same logic Gross Requirements in Periods 4 and 5 develop Net Requirements, Planned Order Receipts, and Planned Order Releases

## Slide 32: Example— School mate products
ITEM: LAPDESK LLC: 0 PERIOD
LOT SIZE: MULT 50 LT: 1 1 2 3 4 5
Gross Requirements 0 60 0 60 0
Scheduled Receipts
Projected on Hand 20
Net Requirements
Planned Order Receipts
Planned Order Releases
ITEM: LAPDESK LLC: 0 PERIOD
LOT SIZE: MULT 50 LT: 1 1 2 3 4 5
Gross Requirements 0 60 0 60 0
Scheduled Receipts
Projected on Hand 20 20 10 10 0 0
Net Requirements 0 40 50
Planned Order Receipts 50 50
Planned Order Releases 50 50
Following the same logic, the Lapdesk MRP matrix is completed as shown

## Slide 33: Example— School mate products
ITEM: PRESSBOARD LLC: 1 PERIOD
LOT SIZE: MIN 100 LT: 1 1 2 3 4 5
Gross Requirements
Scheduled Receipts
Projected on Hand 150
Net Requirements
Planned Order Receipts
Planned Order Releases
ITEM: CLIPBOARD LLC: 0 PERIOD
LOT SIZE: L4L LT: 1 1 2 3 4 5
Planned Order Releases 100 100 100
ITEM: LAPDESK LLC: 0 PERIOD
LOT SIZE: MULT 50 LT: 1 1 2 3 4 5
Planned Order Releases 50 50
ITEM: PRESSBOARD LLC: 1 PERIOD
LOT SIZE: MIN 100 LT: 1 1 2 3 4 5
Gross Requirements 100 100 200 100 0
Scheduled Receipts
Projected on Hand 150
Net Requirements
Planned Order Receipts
Planned Order Releases
ITEM: CLIPBOARD LLC: 0 PERIOD
LOT SIZE: L4L LT: 1 1 2 3 4 5
Planned Order Releases 100 100 100
ITEM: LAPDESK LLC: 0 PERIOD
LOT SIZE: MULT 50 LT: 1 1 2 3 4 5
Planned Order Releases 50 50
x2
x2
x1
x1
x1

## Slide 34: Example— School mate products
ITEM: PRESSBOARD LLC: 1 PERIOD
LOT SIZE: MIN 100 LT: 1 1 2 3 4 5
Gross Requirements 100 100 200 100 0
Scheduled Receipts
Projected on Hand 150 50 50 0 0 0
Net Requirements 50 150 100
Planned Order Receipts 100 150 100
Planned Order Releases 100 150 100
ITEM: CLIPBOARD LLC: 0 PERIOD
LOT SIZE: L4L LT: 1 1 2 3 4 5
Planned Order Releases 100 100 100
ITEM: LAPDESK LLC: 0 PERIOD
LOT SIZE: MULT 50 LT: 1 1 2 3 4 5
Planned Order Releases 50 50

## Slide 35: Example— School mate products
Planned Order Report
PERIOD
ITEM 1 2 3 4 5
Clipboard 100 100 100
Lapdesk 50 50
Pressboard 100 150 100

## Slide 36
Thank You