## Hodgson Algorithm
|  | Project ID/Job | 1 | 2 | 3 | 4 | 5 | 6 | 7
|  | Duration / Processing time | 2 | 6 | 8 | 4 | 14 | 12 | 10
|  | Dude Date | 6 | 30 | 19 | 12 | 24 | 18 | 12
Step 1 | EDD Rule
| EDD Sequence | 1-4-7-6-3-5-2
Define two sets (Early and Late Job)
|  | Set Early - E | 1: (1-4-7-6-3-5-2)
|  | Set Late - L | 1: (empty)
Step 2 | Find out the Tardy Job using EDD Rule
|  | Job | 1 | 4 | 7 | 6 | 3 | 5 | 2
|  | Proce Time | 2 | 4 | 10 | 12 | 8 | 14 | 6
|  | Completion Time | 2 | 6 | 16 | 28 | 36 | 50 | 56
|  | Due Date | 6 | 12 | 12 | 18 | 19 | 24 | 30
|  | Lateness/Tardiness | -4 | -6 | 4 | 10 | 17 | 26 | 26
|  | Tardy(1) & No Tardy (0) | 0 | 0 | 1 | 1 | 1 | 1 | 1
Step 3 |  | There are five tardy jobs. The first tardy job is 7, which is in the third position of the SetEarlie sequence
The job with the longest processing time among the first three jobs is 7. Now remove job 7 from the set E and append it to the set Late L
|  | Set Early - E | 1: (1-4-6-3-5-2)
|  | Set Late - L | 1: 7
Now Revice the completion Time of the Jobs remaining in E
|  | Job | 1 | 4 | 6 | 3 | 5 | 2
|  | Proce Time | 2 | 4 | 12 | 8 | 14 | 6
|  | Completion Time | 2 | 6 | 18 | 26 | 40 | 46
|  | Due Date | 6 | 12 | 18 | 19 | 24 | 30
|  | Lateness/Tardiness | -4 | -6 | 0 | 7 | 16 | 16
|  | Tardy(1) & No Tardy (0) | 0 | 0 | 0 | 1 | 1 | 1
There are three tardy jobs. The first tardy job is 3, which is in the fourth position of the SetEarlie sequence
The job with the longest processing time among the first four jobs is 6. Now remove job 6 from the set E and append it to the set Late L
|  | Set Early - E | 1: (1-4-3-5-2)
|  | Set Late - L | 1: (7-6)
Now Revice the completion Time of the Jobs remaining in E
|  | Job | 1 | 4 | 3 | 5 | 2
|  | Proce Time | 2 | 4 | 8 | 14 | 6
|  | Completion Time | 2 | 6 | 14 | 28 | 34
|  | Due Date | 6 | 12 | 19 | 24 | 30
|  | Lateness/Tardiness | -4 | -6 | -5 | 4 | 4
|  | Tardy(1) & No Tardy (0) | 0 | 0 | 0 | 1 | 1
There are two tardy jobs. The first tardy job is 5, which is in the fourth position of the SetEarlie sequence
The job with the longest processing time among the first four jobs is 5. Now remove job 5 from the set E and append it to the set Late L
|  | Set Early - E | 1: (1-4-3-2)
|  | Set Late - L | 1: (7-6-5)
Now Revice the completion Time of the Jobs remaining in E
|  | Job | 1: 1; 2: 4; 3: 3; 4: 2
|  | Proce Time | 1: 2; 2: 4; 3: 8; 4: 6
|  | Completion Time | 1: 2; 2: 6; 3: 14; 4: 20
|  | Due Date | 1: 6; 2: 12; 3: 19; 4: 30
|  | Lateness/Tardiness | 1: -4; 2: -6; 3: -5; 4: -10
|  | Tardy(1) & No Tardy (0) | 1: 0; 2: 0; 3: 0; 4: 0
From the table all the jobs are non-tardy. Hence we reached the optimal sequence in SetEarly
Now merge E and L to get the complete sequence
|  | Final Sequecne | 1: (1-4-3-2-7-6-5)
| Job | 1 | 4 | 3 | 2 | 7 | 6 | 5 |  | Makespan | 56
| Proce Time | 2 | 4 | 8 | 6 | 10 | 12 | 14 |  | Max Tardiness | 32
| Completion Time | 2 | 6 | 14 | 20 | 30 | 42 | 56 |  | Number of Late Jobs | 3
| Due Date | 6 | 12 | 19 | 30 | 12 | 18 | 24 |  | Mean Flow Time | 24.2857
| Lateness/Tardiness | -4 | -6 | -5 | -10 | 18 | 24 | 32 |  | Total Tardiness | 74
| Tardy(1) & No Tardy (0) | 0 | 0 | 0 | 0 | 1 | 1 | 1
|  |  | Makespan | Max Tardiness | Number of Late Jobs | Mean Flow Time | Total Tardiness
|  | SPT | 56 | 32 | 4 | 24 | 75
|  | LPT | 56 | 50 | 6 | 40 | 169
|  | EDD | 56 | 26 | 5 | 27.7143 | 83
|  | FCFS | 56 | 44 | 4 | 26 | 90
|  | Hodgson Algo | 56 | 32 | 3 | 24.2857 | 74